## Overview
MEDCOMMS / ACCOUNT EXECUTIVE
PORTFOLIO CASE STUDY 01 ¦ Fictional scenario · independent skills demonstration
Reporting snapshot | 2026-11-10
CASE BRIEF
Client | Asteria Bio — fictional biotechnology organisation
Campaign | Non-promotional healthcare-professional webinar: interpreting published hypertension evidence
Objectives | Accurate and accessible scientific education; on-time delivery within approved budget
Deliverables | 18-slide educational presentation, speaker brief, live webinar, post-event outcomes report
AE responsibility | Coordinate workstreams, prepare updates, track finances, document decisions and escalate delivery risks
Governance | Scientific/medical review required; Account Manager approves client commitments and scope changes
LIVE SNAPSHOT — formulas calculate from the project tabs
COMPLETED TASKS |  | TASKS NEED ATTENTION | FORECAST COST | FORECAST VARIANCE
3 |  | 5 | 11670 | 1780
DELIVERY DECISION / RECOMMENDATION
09 Nov: Client requests three additional slides while the first draft is late. The Account Manager is unavailable for two hours.
Act as the AE: verify writing and review capacity, quantify scope impact, log the request, and brief the Account Manager.
Do not promise the client a new deadline, budget or revised scope until the Account Manager authorises it.
Update the tracker, budget, RAID and change-control logs with your proposed resolution.
Use these artifacts to write a 1-page case study: situation → your judgement → decisions → expected outcome.
NEXT STEP → Open 'Delivery Dashboard' for the live task and finance summary; update editable statuses and dates in 'Project Tracker'.
PORTFOLIO INTEGRITY: All people, costs, communications and project outcomes are simulated. No employment or client engagement is implied.

## Project Tracker
01 / PROJECT DELIVERY
Scenario milestone dates · editable statuses and revised deadlines
ID | Task / deliverable | Team | Baseline due | Revised due | Status | Owner | Risk flag* | Dependencies / AE next action | Days left | Slip (days) | AE follow-up
P01 | Kick-off and confirm brief | Accounts | 2026-11-02 | 2026-11-02 | Complete | AE | Complete | Record agreed objectives / audience |  | 0 | Closed
P02 | Scope & budget approval | Accounts | 2026-11-03 | 2026-11-03 | Complete | AM | Complete | Approved brief and budget required |  | 0 | Closed
P03 | Literature source pack | Scientific | 2026-11-05 | 2026-11-05 | Complete | Writer | Complete | Use credible published sources |  | 0 | Closed
P04 | 18-slide first draft | Scientific | 2026-11-09 | 2026-11-12 | In progress | Writer | Due soon | Writer capacity and revised timeline | 2 | 3 | Confirm next step
P05 | Scientific & accuracy review | Review | 2026-11-11 | 2026-11-14 | Blocked | Reviewer | Blocked | Requires slide draft; escalate | 4 | 3 | Resolve dependency
P06 | Design & formatting | Creative | 2026-11-13 | 2026-11-19 | Not started | Designer | At risk | Needs reviewed copy | 9 | 6 | Recheck capacity / plan
P07 | Client content review | Client | 2026-11-17 | 2026-11-21 | Not started | AM | At risk | Send only after QA | 11 | 4 | Recheck capacity / plan
P08 | Final medical & client approval | Review | 2026-11-20 | 2026-11-23 | Not started | AM | At risk | Medical/legal process as needed | 13 | 3 | Recheck capacity / plan
P09 | Speaker briefing & rehearsal | Events | 2026-11-23 | 2026-11-23 | Not started | AE | On track | Confirm speaker and materials | 13 | 0 | Monitor
P10 | Webinar logistics & dry run | Events | 2026-11-24 | 2026-11-24 | Not started | AE | On track | Platform, joining instructions, checks | 14 | 0 | Monitor
P11 | HCP educational webinar | Events | 2026-11-25 | 2026-11-25 | Not started | Team | On track | Final content and platform approval | 15 | 0 | Monitor
P12 | Post-webinar outcomes report | Accounts | 2026-11-27 | 2026-11-27 | Not started | AE | On track | Attendance / feedback metrics | 17 | 0 | Monitor
* Risk flags use the fictional reporting date on Overview (B5), not TODAY(). Dates and status are editable blue cells.
Control note: changes to dates or status update the delivery dashboard and Gantt automatically.
At risk = 3+ days of schedule slip and not due within the next 3 days; blocked/overdue always take precedence.

## Budget
02 / PROJECT FINANCES
Illustrative internal budget (not a quote) · change requests require approval
Workstream | Plan hours | Rate (£/hr) | Budget (£) | Used hours | Spent (£) | Hours to go | Estimate at completion (£) | Variance (£) | Action
Medical writing | 30 | 105 | 3150 | 20 | 2100 | 17 | 3885 | 735 | Overrun likely—confirm scope
Scientific review | 12 | 135 | 1620 | 4 | 540 | 12 | 2160 | 540 | Review capacity bottleneck
Graphic design | 20 | 85 | 1700 | 0 | 0 | 21 | 1785 | 85 | Pending approved copy
Account coordination | 26 | 70 | 1820 | 14 | 980 | 18 | 2240 | 420 | Additional client meetings
Event production | 10 | 95 | 950 | 0 | 0 | 10 | 950 | 0 | Fixed webinar date
Supplier platform | 1 | 650 | 650 | 0 | 0 | 1 | 650 | 0 | Check contract / PO
TOTAL |  |  | 9890 |  | 3620 |  | 11670 | 1780
INTERPRETATION / ACCOUNT EXECUTIVE DECISION
Budget above is based on fictional hourly charge-out rates. Actual agency costs and client billing could use different models.
The AE tracks forecast versus authorised budget and flags emerging overruns—not independently approves extra spending.
For additional client slides: estimate incremental writer/reviewer/design hours; propose scope trade-off or additional budget via the Account Manager.
A change is not agreed until the authorised parties document approval. Track versions and commercial impact.

## Risks & Issues
03 / RISKS & ISSUES
Proactive risk identification, ownership, escalation and mitigation
ID | Type | Risk or issue | Likelihood | Impact | Owner | Current status | Mitigation / next step | Escalate?
R01 | Issue | First slide draft delayed, jeopardising downstream medical review | High | High | AE / Writer | Open | Confirm realistic writing capacity; prioritise critical path; inform AM | Yes
R02 | Risk | Client adds 3 slides after brief approval | High | High | AM | Open | Assess extra scope, hours, approvals and deadline impact | Yes
R03 | Risk | Scientific claim lacks traceable literature source | Medium | High | Reviewer | Open | Evidence table + references; block release until signed off | Yes
R04 | Risk | Multiple revisions create wrong-version delivery | Medium | Medium | AE | Mitigating | Central version register, owner and approvals record | No
R05 | Risk | Webinar platform rehearsal delayed | Low | Medium | Events | Monitoring | Book dry run and backup conferencing route | No

## Change Control
04 / CHANGE CONTROL
Treat additional client requests as impact-assessment and approval decisions
Change ID | Received | Client request | Initial assessment | Estimated cost (£) | Time impact (days) | Decision owner | Approval status | AE next step
CR-001 | 2026-11-09 | Add three new scientific comparison slides | Extra research, writing, review and design | 900 | 2 | Account Manager | Proposed - Awaiting Approval | Recommend scoped change request to AM. Confirm delivery capacity, medical review and client agreement before proceeding.
CR-002 | 2026-11-10 | Revise chart data and visual style | Medical verification required; limited design impact | 325 | 0 | Account Manager | In review | Validate source and designer effort; log medical review
DECISION OPTIONS TO PREPARE FOR ACCOUNT MANAGER
1 · Keep delivery date |  | Reprioritise non-critical work; check actual spare capacity and QA protection; do not assume overtime is free.
2 · Agree revised deadline |  | Quantify critical-path impact and request AM permission to discuss extension with client.
3 · Adjust scope |  | Ask whether existing slides could be adapted rather than introducing three wholly new scientific slides.
4 · Additional funding |  | Provide documented revised estimate; get commercial approval before adding chargeable work.

## Contact Report
05 / CONTACT REPORT
Sample meeting record and escalation log · fictional clients and messages
Date | Audience | Topic | Update / action recorded | Owner | Due | Status | AM sign-off
2026-11-02 | Internal + client | Kick-off | Confirm scope: 18 slides; medical review; webinar on 25 Nov | AE | 2026-11-03 | Done | Yes
2026-11-06 | Writer / reviewer | First draft progress | Request detailed forecast, review buffer and missing evidence list | AE | 2026-11-07 | Done | Not needed
2026-11-09 | Internal | Three-slide change | Collect writer, reviewer and designer effort; calculate budget/time options | AE | 2026-11-10 | In progress | Pending
2026-11-10 | Account Manager | Urgent escalation | First draft late; scientific review blocked. Present 3 recovery scenarios and approval needs | AE | 2026-11-10 | Pending | Pending
2026-11-10 | Client | Receipt acknowledgement | Acknowledge request, confirm team assessing feasibility; avoid unapproved promise | AM | 2026-11-10 | Draft | Pending
SAMPLE DRAFT / INTERNAL ESCALATION NOTE — adapt into your own words
Subject: Webinar slides — delivery risk and additional client request
The writing team has flagged a delay to the 18-slide draft, which affects the planned review window. The client has also requested three extra slides beyond the approved scope.
I am confirming revised effort estimates with the writer, medical reviewer and designer, including the impact on quality review and the live webinar date.
My recommendation is to present the client with a scoped set of options after your review: replace existing content, approve additional time/budget, or move the content to post-event materials.
I have logged the issues in the project tracker, RAID log and change register. I will not commit to revised costs or timings before your approval.

## Sources & Notes
06 / SOURCES & USE
Reference sources, model assumptions and transparency statement
Reference | What it establishes | Source URL | Checked / context
IPG Health Fuel | Training route accepts career changers; project coordination, timelines and financial trackers | https://jobs.weekday.works/ipg-health-medical-communications-associate-account-executive | Role text; availability not confirmed
BOLDSCIENCE AE | Account executive responsibilities include status reports, meeting logs, client liaison and budget tracking | https://builtinlondon.uk/job/account-executive/11311563 | 2026 job description
BBH Graduate / Entry Health | Early-career health account work includes finances, deadlines, commercial and client coordination | https://careers.publicisgroupe.com/PS-SignUp-27/jobs/174678 | 18 Sep 2026 posting
Healthcare Communications Association | Independent portfolio development encouraged for sector entry | https://healthcomms.careers/Careers-Information/Starting-your-career | Career guidance
PROJECT METHODOLOGY & DISCLOSURE
Independent project simulation based on a fictional medical communications webinar brief.
The model compares baseline vs revised schedules, forecast budgets and resource-recovery options.
All estimated rates, events, client requests and internal communications are illustrative.
This is not paid employment, verified client delivery or evidence of a real clinical review.
No real patient data, fabricated scientific citations or claims of third-party endorsement are included.

## AE Workshop
ACCOUNT EXECUTIVE ¦ PROJECT DECISION RECORD
CASE 01 • Fictional medical communications project • documented delivery assessment
THE LIVE ACCOUNT SNAPSHOT ¦ 10 NOV 2026
Client / event | Asteria Bio (fictional) | Webinar | 2026-11-25
Approved budget | 9890 | Forecast at completion | 11670
Forecast overspend | 1780 | Overspend (%) | 18%
BUDGET NOTE: Change requests £900 and £325 are estimates awaiting approval. Check for overlap with the base forecast before adding them.
WHAT HAS HAPPENED
09 NOV • Medical writer says the first draft needs another three days; scientific review is blocked.
09 NOV • Client requests three additional slides; estimated £900 extra and two more days (not authorised).
10 NOV • Client also requests a chart revision; source accuracy must be checked (£325 estimate).
CONSTRAINT • The Account Manager is unreachable for two hours. The webinar date is fixed. Review is currently revised to SAT 14 NOV.
DELIVERY ASSESSMENT ¦ ACTIONS, COMMUNICATION AND RECOMMENDATIONS
01 — FIRST 30 MINUTES Who do you contact first, and what exactly do you need to verify before proposing a solution? |  | Contact the medical writer to identify the cause of the delay, confirm the revised delivery date and estimate the additional work required. Consult the design and medical review teams to assess resource availability and scheduling constraints. Document the risks and prepare an update for the Account Manager before committing to changes.
02 — CRITICAL PATH What is most at risk? Check revised deadlines, scientific approval, and whether the Saturday review is feasible. |  | The biggest risk is the delayed draft disrupting scientific review and design. The revised Saturday review date also requires confirmation of reviewer availability. Any missed approval could affect the fixed webinar deadline.
03 — OPTIONS FOR YOUR AM Provide two realistic options, covering time, additional cost, scientific review and client expectations. |  | Option A: Use the existing design team to minimise additional costs, provided the revised schedule can accommodate scientific review and final approvals. Option B: Consider freelance design support for £600 to protect the review deadline, subject to budget approval and confirmation of scientific quality requirements. Recommend Option B if internal resources cannot meet the necessary approval dates.
04 — INTERNAL UPDATE Draft a concise four-sentence message to your Account Manager: facts, risks, options and approval needed. |  | The medical writer has reported a three-day delay, affecting our scientific review and subsequent design schedule. The client has also requested three additional slides, creating additional resource and budget pressures. I've consulted the relevant teams and identified internal scheduling adjustments and freelance design support as potential solutions. I recommend reviewing these options together before approving expenditure or confirming any revised deadlines to the client.
05 — CLIENT ACKNOWLEDGEMENT Draft a short professional client reply without promising costs, dates or revised scope before approval. |  | Thank you for sharing your request for the three additional slides. We understand the importance of incorporating the latest clinical evidence into the presentation. I'll coordinate with our medical writing, review and design teams to assess the requirements and potential impact on the existing project scope and timeline. We'll follow up once the proposed approach has been reviewed internally.
06 — DOCUMENTATION Which three project records will you update, and what would you change in each? |  | Project Tracker: Update revised deadlines, task statuses, dependencies and responsible team members. Risk Register: Record the writing delay, potential missed review deadlines, budget overrun and proposed mitigation actions. Change Control: Document the additional three-slide request, estimated costs, impact on resources and approval status. I would also update the client contact report to maintain an accurate record of communications and agreed next steps.
QUALITY GATE ¦ DOCUMENTED VERIFICATION STATUS
Scientific claims have source references and qualified scientific / medical review. |  |  | Not reviewed
Any new scope is costed and its effect on review and design timelines is understood. |  |  | Needs work
Revised dates are actually achievable (not weekends without confirmed coverage). |  |  | Needs work
Account Manager has reviewed/authorised external commitments and commercial changes. |  |  | Not reviewed
Tracker, risk register, change log and client contact report all tell the same story. |  |  | Needs work
PORTFOLIO ETHICS • This is an independent simulation; figures, clients, approvals and responses are fictional.

## Recovery Model
MEDCOMMS / DELIVERY RECOVERY MODEL
PORTFOLIO 01 • Asteria Bio (fictional) • 3 additional hypertension evidence slides
01 ¦ PROJECT FINANCES & DELIVERY CONSTRAINTS
Approved budget | 9890 |  | Current forecast | 11670 |  | Current overrun | 1780
Medical review slot | 2026-11-20 |  | Webinar date | 2026-11-25 |  | Original slides | 18
Approval owner | Account Manager |  | Requested extra slides | 3 |  | Review scope | Extra slides only
02 ¦ RECOVERY OPTIONS — DELIVERY AND FINANCIAL COMPARISON
Design option | Slides delivered | Extra fee (£) | Revised forecast | Variance vs plan | Days to review | Medical review? | Days to webinar | AE next action
Existing designers | 2026-11-23 | 0 | 11670 | 1780 | -3 | MISSES REVIEW | 2 | Escalate review conflict
Freelance support | 2026-11-19 | 600 | 12270 | 2380 | 1 | FEASIBLE | 6 | Confirm quality + AM approval
03 ¦ FORMULA-BASED RECOMMENDATION
Feasible options | 1 |  | Least-cost feasible | Freelance support |  | Approval required | Account Manager
Selected forecast | 12270 |  | Selected variance | 2380 |  | Review buffer (days) | 1
04 ¦ ACCOUNT EXECUTIVE RECOMMENDATION
This 20 November slot is for the 3 extra slides; the original draft review is tracked separately in Project Tracker.
Checks before approval | Confirm review capacity, final QA, availability of the freelancer and whether their £600 fee overlaps with forecast costs.
Your recommendation | Preferred conditional option: freelance design (£600) if capacity, scientific review and quality checks can be confirmed. Current internal delivery (23 Nov) misses the additional-slides review slot (20 Nov); freelance delivery (19 Nov) leaves one calendar day before review. This raises the forecast from £11,670 to £12,270, a £2,380 variance against the £9,890 approved plan. The Account Manager must assess affordability, confirm whether the £600 overlaps existing design cost estimates, verify actual reviewer availability and agree any client-facing scope/cost position before commitment. The 25 Nov webinar date remains fixed; scheduling and approval risks remain unresolved.
MODEL NOTES & GOVERNANCE
Scenario date and fee assumptions are editable; calculated figures link to budget and tracker.
The £600 freelancer fee is added to the existing forecast: double-counting must be checked before requesting approval.
A feasible date is not approval: scientific accuracy, version control and client sign-off still apply.
All figures, brands and client scenarios are fictional and presented for skills demonstration.

## Delivery Dashboard
DELIVERY CONTROL / HEALTHCARE WEBINAR
Fictional Asteria Bio project • Formula-driven snapshot linked to Project Tracker, Budget and Recovery Model
Snapshot date | 2026-11-10 |  | Webinar | 2026-11-25 |  | Data mode | SIMULATED
01 ¦ DELIVERY PULSE
COMPLETED TASKS |  |  | OPEN / ACTIVE |  |  | NEED ATTENTION
| 3 |  |  | 2 |  |  | 5
DUE WITHIN 7 DAYS |  |  | MAX SLIPPAGE |  |  | DAYS TO WEBINAR
| 2 |  |  | 6 |  |  | 15
02 ¦ COMMERCIAL HEALTH
APPROVED BUDGET |  |  | FORECAST TOTAL |  |  | PROJECTED OVERSPEND
| 9890 |  |  | 11670 |  |  | 1780
03 ¦ MILESTONE GATES & NEXT STEPS | [5 empty] | 04 ¦ TASK STATUS MIX
ID | Deliverable | Revised due | Risk flag | Slip (days) | Account Executive follow-up | Stage | Tasks
P04 | 18-slide first draft | 2026-11-12 | Due soon | 3 | Confirm next step | Complete | 3
P05 | Scientific & accuracy review | 2026-11-14 | Blocked | 3 | Resolve dependency | In progress | 1
P06 | Design & formatting | 2026-11-19 | At risk | 6 | Recheck capacity / plan | Blocked | 1
P07 | Client content review | 2026-11-21 | At risk | 4 | Recheck capacity / plan | Not started | 7
P08 | Final medical & client approval | 2026-11-23 | At risk | 3 | Recheck capacity / plan
P11 | HCP educational webinar | 2026-11-25 | On track | 0 | Monitor
05 ¦ PROJECT CONTROLS / HOW TO USE
01. Edit Status (column F) or Revised due (column E) on Project Tracker. Blue cells indicate inputs.
02. Risk flags use the fictional 10 November 2026 reporting date. Overdue and Blocked take priority.
03. The dashboard reads from source sheets. This workbook is a simulated independent portfolio case study.
04. Only the Account Manager may approve client commitments, revised scope or additional expenditure.
NEW ¦ Open 'Gantt Timeline' for a formula-driven day-by-day schedule and dependency warnings.

## Gantt Timeline
PROJECT 01 / DELIVERY GANTT & DEPENDENCIES | [10 empty] | HYPERTENSION HCP WEBINAR ¦ 02 NOV — 03 DEC 2026
ASTERIA BIO • fictional client • schedule and gates linked to Project Tracker | [10 empty] | ◆ revised due │ original due ■ work window amber = revised schedule
SLIPPED TASKS |  | 5 |  | GATE CONFLICTS |  | 2 |  | LATEST DUE |  | 2026-11-27
SCHEDULE CONTROL ¦ REVISED DATES AND DEPENDENCY CHECKS | [10 empty] | ■ active work │ baseline deadline ◆ revised milestone • automatic dependency conflicts
01 TASK SCHEDULE / PROJECT GATES | [10 empty] | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5
ID | DELIVERABLE | TEAM | START ✎ | ORIGINAL DUE | REVISED DUE | STATUS | GATE AFTER | SLIP | GATE CHECK | OWNER | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu
[11 empty] | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-22 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-28 | 2026-11-29 | 2026-11-30 | 2026-12-01 | 2026-12-02 | 2026-12-03
P01 | Kick-off and confirm brief | Accounts | 2026-11-02 | 2026-11-02 | 2026-11-02 | Complete |  | 0 | — | AE | bar: 2026-11-02
P02 | Scope & budget approval | Accounts | 2026-11-03 | 2026-11-03 | 2026-11-03 | Complete | P01 | 0 | OK | AM | bar: 2026-11-03
P03 | Literature source pack | Scientific | 2026-11-04 | 2026-11-05 | 2026-11-05 | Complete | P02 | 0 | OK | Writer | bar: 2026-11-04 to 2026-11-05
P04 | 18-slide first draft | Scientific | 2026-11-06 | 2026-11-09 | 2026-11-12 | In progress | P03 | 3 | OK | Writer | 2026-11-06: ■; 2026-11-07: ■; 2026-11-08: ■; 2026-11-09: │; 2026-11-10: ■; 2026-11-11: ■; 2026-11-12: ◆
P05 | Scientific & accuracy review | Review | 2026-11-14 | 2026-11-11 | 2026-11-14 | Blocked | P04 | 3 | OK | Reviewer | bar: 2026-11-11; 2026-11-14
P06 | Design & formatting | Creative | 2026-11-16 | 2026-11-13 | 2026-11-19 | Not started | P05 | 6 | OK | Designer | 2026-11-13: │; 2026-11-16: ■; 2026-11-17: ■; 2026-11-18: ■; 2026-11-19: ◆
P07 | Client content review | Client | 2026-11-20 | 2026-11-17 | 2026-11-21 | Not started | P06 | 4 | OK | AM | 2026-11-17: │; 2026-11-20: ■; 2026-11-21: ◆
P08 | Final medical & client approval | Review | 2026-11-22 | 2026-11-20 | 2026-11-23 | Not started | P07 | 3 | OK | AM | 2026-11-20: │; 2026-11-22: ■; 2026-11-23: ◆
P09 | Speaker briefing & rehearsal | Events | 2026-11-23 | 2026-11-23 | 2026-11-23 | Not started | P08 | 0 | CONFLICT | AE | bar: 2026-11-23
P10 | Webinar logistics & dry run | Events | 2026-11-23 | 2026-11-24 | 2026-11-24 | Not started | P08 | 0 | CONFLICT | AE | bar: 2026-11-23 to 2026-11-24
P11 | HCP educational webinar | Events | 2026-11-25 | 2026-11-25 | 2026-11-25 | Not started | P10 | 0 | OK | Team | bar: 2026-11-25
P12 | Post-webinar outcomes report | Accounts | 2026-11-26 | 2026-11-27 | 2026-11-27 | Not started | P11 | 0 | OK | AE | bar: 2026-11-26 to 2026-11-27
02 DELIVERY LOGIC / WHAT THE TIMELINE TELLS YOU
GATE AFTER is the primary task that should finish before this task starts. CONFLICT means the predecessor's revised due date is on or after this task's scheduled start.
Dependencies are planning checks, not evidence that review slots, resourcing or approvals are confirmed.
The current plan retains unresolved downstream conflicts and weekend availability risks pending approval.
Recovery Model is a separate what-if comparison; it does not automatically commit its scenario to this schedule.
Calendar days are shown, including weekends; check working-day availability and medical approvals before making commitments.